## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| trading center | Mjd.D | 2020-06-06 | 2020-06-25 |  | 100% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| create invoice(sprint) |  | Mjd.D |  | 2020-06-06 | 2020-06-10 | 4 | Completed
| selling invoice (feature) |  | Jullnar Sh. |  | 2020-06-07 | 2020-06-12 | 5 | Completed
| buying invoice (feature) |  | Jullnar Sh. |  | 2020-06-09 | 2020-06-13 | 4 | Completed
| add person to the system (sprint) |  | Mjd D. |  | 2020-06-16 | 2020-06-24 | 8 | Completed
| add customer (feature) |  | Rafah A. |  | 2020-06-16 | 2020-06-17 | 1 | Completed
| add trader (feature) |  | Rafah A. |  | 2020-06-17 | 2020-06-21 | 4 | Completed
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.